## Sheet 1
GSR/4610 Finch PM KPI Matrix
Sr. No. | KPI | Measurement Method | Frequency | Target / Threshold | Actual (%) | Weight (%) | Scoring Method | Traffic-Light Indicator
1 | Site Clerk (Project Manager) 1. Site Inspection & Field Monitoring - 10 2. Documentation & Reporting - 7.5 3. Compliance & Regulatory Coordination - 7.5 4. Coordination & Communication - 10 5. Commercial & Progress Validation -05 | % of duties completed as mentioned in the scope duties statement | Monthly | ≥95% compliance |  | 40 | (Actual % ÷ Target %) × Weight
2 | Project Management Plan | Completeness check; % of updates delivered on time | Quarterly | ≥95% completeness; ≤5% variance |  | 10 | (Actual % ÷ Target %) × Weight | Green ≥90%, Yellow 75–89%, Red <75%
3 | Financial Reporting - Cost Tracking and Variance | Accuracy of reports; variance forecast vs actual spend | Monthly | ≤5% variance; 100% timely submission |  | 5 | (Target – Variance %) × Weight | Green ≥90%, Yellow 75–89%, Red <75%
4 | Schedule Status Updates & Variance Tracking | % deviation from contract baseline schedule. | Monthly | ≥95% accuracy; 100% completeness |  | 5 | (Actual % ÷ Target %) × Weight | Green ≥90%, Yellow 75–89%, Red <75%
5 | Sub-Consultant Management | Compliance with procurement process; % of reports reviewed | Monthly | 100% compliance; ≥90% timely reviews |  | 5 | (Actual % ÷ Target %) × Weight | Green ≥90%, Yellow 75–89%, Red <75%
6 | Resource Management | Schedule variance; budget variance | Monthly | ≤5% variance |  | 5 | (Target – Variance %) × Weight | Green ≥90%, Yellow 75–89%, Red <75%
7 | Quality Control & Commissioning | % of tests completed; % of deficiencies resolved | As per the Contract Scope requirements | ≥95% completion; ≤5% unresolved |  | 7.5 | (Actual % ÷ Target %) × Weight | Green ≥90%, Yellow 75–89%, Red <75%
8 | Meetings & Stakeholder Engagement | % of meetings held; % of minutes issued within 48 hrs | Weekly, Bi-weekly, Monthly | ≥95% compliance |  | 7.5 | (Actual % ÷ Target %) × Weight | Green ≥90%, Yellow 75–89%, Red <75%
9 | Document Control | % of documents logged, reviewed, distributed correctly | Bi-weekly | ≥95% accuracy; 100% version control |  | 10 | (Actual % ÷ Target %) × Weight | Green ≥90%, Yellow 75–89%, Red <75%
10 | Close-out & Handover | % of close-out deliverables submitted on time; % of deficiencies resolved before handover | As per the Contract Scope requirements | ≥95% completeness; 100% timely submission |  | 5 | (Actual % ÷ Target %) × Weight | Green ≥90%, Yellow 75–89%, Red <75%
100
Scoring Framework
Monthly Score = Σ (Weighted KPI Scores)
Performance Rating Bands:
≥95% → excellent performance
85–94% → Meets requirements (neutral)
60–84% → Below requirements
<60% → Unsatisfactory
Note: The City may use these earned KPI scores to evaluate the pre‑qualification status of the Construction Manager for future similar project bids.
Contract-Linked Definitions of Measurement Methods
1. Completeness Check
Definition: Verification that all contractually required deliverables (plans, registers, logs, reports) are produced and updated.
Contract Link: Scope of Work clauses requiring submission of Project Management Plan, Risk Register, Quality Plan, Communication Plan, etc.
Measurement: % of deliverables submitted vs. total required under contract.
Example: If 18 out of 20 required contract deliverables are submitted, completeness = 90%.
2. Accuracy Report
Definition: Assessment of whether reports and certifications are consistent with contract requirements, tender documents, and financial records.
Contract Link: Clauses requiring accurate monthly financial reports, payment certifications, and status reports.
Measurement: % of reports issued without discrepancies against contract-defined standards.
Example: If 9 out of 10 reports meet contractual accuracy standards, accuracy = 90%.
3. Schedule Variance
Definition: Difference between contractually committed schedule milestones and actual completion dates.
Contract Link: Baseline schedule approved in contract, including milestones for design, permits, GMP, construction, commissioning, and close-out.
Measurement: % deviation from contract baseline schedule.
Formula: (Planned–Actual)÷Planned×100%(Planned – Actual) ÷ Planned × 100%.
Example: Planned milestone = 30 days, actual = 33 days → variance = -10%.
4. Cost Variance
Definition: Difference between contract budget and actual spend.
Contract Link: Clauses requiring cost tracking, variance reporting, and adherence to GMP.
Measurement: % deviation from contract budget.
Example: Budget = $1M, actual = $1.05M → variance = -5%.
5. Timeliness
Definition: Ability to deliver contract-required reports and milestones by agreed deadlines.
Contract Link: Clauses requiring monthly reports, financial certifications, and status updates.
Measurement: % of deliverables submitted on or before contractual due dates.
Example: 8 out of 10 reports submitted on time → timeliness = 80%.
6. Risk & Issue Management
Definition: Effectiveness in managing risks/issues as per contract obligations.
Contract Link: Clauses requiring maintenance of Risk Register and Issue Log.
Measurement: % of risks/issues resolved within contractually defined timelines.
Example: 12 out of 15 risks mitigated within timeframe → 80%.
7. Quality Control
Definition: Extent to which deliverables meet contract specifications and pass QA/QC checks.
Contract Link: Clauses requiring compliance with Quality Plan and inspection protocols.
Measurement: % of inspections/tests passed without deficiencies.
Example: 95 out of 100 inspections passed → quality = 95%.
8. Stakeholder Engagement
Definition: Effectiveness of communication and coordination with stakeholders as per contract requirements.
Contract Link: Clauses requiring stakeholder registers, meeting minutes, and communication plans.
Measurement: % of scheduled meetings held, minutes issued within 48 hours, and stakeholder feedback addressed.
Example: 10 meetings scheduled, 9 held with minutes issued → 90%.
9. Document Control
Definition: Accuracy and reliability of project documentation management.
Contract Link: Clauses requiring document management systems, version control, and compliance with City documentation standards.
Measurement: % of documents logged, reviewed, and distributed correctly.
Example: 950 out of 1,000 documents managed correctly → 95%.
10. Close-out & Handover
Definition: Completion of all final deliverables required by contract (as-builts, O&M manuals, warranties, training, occupancy permits, lessons learned).
Contract Link: Clauses requiring close-out documentation, warranty schedules, and handover protocols.
Measurement: % of close-out deliverables submitted and accepted by client.
Example: 18 out of 20 deliverables submitted and approved → 90%.