## Instructions
4610 Finch & GSR PM nRFP Resource Management Plan Instructions |  | Proponent Information
Company Name:
nRFP #: | Doc5587239263 | Contact Name:
nRFP Title: | George St Revitalization - Project Management Consultant nRFP | Contact Phone #:
Contact Email:
General Information and Conditions:
• Please provide your company and contact information in the GREEN highlighted fields on this tab.
• The 'Project Tasks' section is for information only and does not require supplier input.
• The information provided in the 'Resource Management Plan' tab is an estimated only and is subject to change.
Resource Management Plan Form Information:
• All hours are to be considered a blended team workload allocation that represents the level of effort and hours associated with the outlined schedule.
• Proponents shall review each tab in it's entirety, in addition to the Scope of Work and nRFP documents included in Ariba.
• Proponents shall submit information for all noted items in the 'Resource Management Form' tab.
• Proponents are to submit this Resource Management Plan Form without any changes to the structure / locked data. Any submission received without following the prescribed format may not be considered for evaluation and award.
• This Resource Management Plan Form contains two (2) tabs, including this Instructions tab.
Resource Management Plan Tab:
• Please enter information in GREEN cells. BLUE cells are calculated via formulas.
• Suppliers do not need to add any information to the 'Project Tasks' section. This section is for information only and indicates the anticipated schedule that the project will be following.
• Suppliers are responsible for completing the following table within the Resource Management Plan tab:
1) Suppliers must provide the total 'Hours' for each Phase noted under the 'Overall Summary Total by Phases' section.
• The total 'Hours Allocated' for Phases 1-3 in the 'Overall Summary Total by Phases' must be equal to the total hours indicated for Phases 1-3 in the Part 5 - Pricing Form.
• If hours aren't required for a given field, suppliers shall enter "0" into the respective field. Please do not leave fields blank.

## Resource Management Plan
George Street Revitalization Project Resource Management Form (Include but not Limited to the Following) | [22 empty] | 2026 | [51 empty] | 2027 | [50 empty] | 2028 | [50 empty] | 2029 | [50 empty] | 2030
[11 empty] | Q4 | [11 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [11 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [11 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [11 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [11 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  | A |  |  |  | S |  |  |  |  | O |  |  |  | N |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  |  | A |  |  |  | M |  |  |  | J |  |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  | A |  |  |  | M |  |  |  |  | J |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  | A |  |  |  | M |  |  |  |  | J |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  | A |  |  |  | M |  |  |  |  | J |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  | A |  |  |  | M |  |  |  |  | J |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D
|  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
PROJECT TASKS
Phase 1 - Design Review and Contract Documents
Drawings and Specifications | bar: M 4 to J 27
Submit 50% CD's for Client, TGS Reviewer and CM Formal Review | bar: J 13 to A 3
Community Consultation | bar: A 3
VE based on Update to Class B Level Cost Estimate at 50% of CD's Issued by CM | bar: A 3 to A 10
Submit 75% CD's for Client and CM Formal Review | bar: A 17 to S 21
VE based on Class A Level Cost Estimate at 75% of CD's Issued by CM | bar: S 28 to O 5
Update Class A Level Cost Estimate at 95% of CD's Issued by CM | bar: O 12 to N 2
VE based on Update Class A Level Cost Estimate at 95% of CD's Issued by CM | bar: N 9 to N 16
Submit 100% CD's for Client with Formal Presentation to Stakeholders and CM Formal Review | bar: N 23 to N 30
Submit Final CD's to Client and CM to Proceed to Finalizing GMP | bar: D 7
Community Consultation | bar: D 7
Attendance at pre-bid meetings | bar: F 1
Response to Bidding Enquiries and Issue Addenda | bar: O 12; O 26; N 9; N 23; D 14 to D 21; J 11 to J 18; F 8 to J 5
GMP Pricing and CM Negotiations | bar: M 24 to J 26
Phase 2 - Construction
Assume the following tasks throughout the CA period: refer detailed scope of work | bar: S 7 to M 29
Attend all site meetings (assume bi-weekly throughout construction)
Produce "Issued for Construction" set | bar: S 7 to S 14
Review and Approve All Submittals
Respond to RFI's
Issue SI's, CCN's, CO's and CD's as Required
General Review
Payment Certification
Deficiency Review
Record Drawings
Project Close Out
Community Consultation | bar: A 17
FF&E
FF&E selection | bar: O 5 to F 1
Procurement | bar: F 8 to J 14
Installation | bar: J 21 to D 28
Phase 3 - Project Commissioning, Deficiency Review, Close-out
Project Commissioning | bar: A 5 to J 25
Deficiency Review | bar: A 5 to J 25
Close-out | bar: D 7 to M 29
George Street Revitalization Project Resource Management Form (Include but not Limited to the Following) |  | J 5: 2026; J 4: 2027; J 4: 2028; J 4: 2029; J 4: 2030
[11 empty] | Q4 | [11 empty] | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [11 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [11 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [11 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [11 empty] | Q2 | [12 empty] | Q3 | [12 empty] | Q4
|  | A |  |  |  | S |  |  |  |  | O |  |  |  | N |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  |  | A |  |  |  | M |  |  |  | J |  |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  | A |  |  |  | M |  |  |  |  | J |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  | A |  |  |  | M |  |  |  |  | J |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  | A |  |  |  | M |  |  |  |  | J |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D |  |  |  | J |  |  |  | F |  |  |  | M |  |  |  | A |  |  |  | M |  |  |  |  | J |  |  |  | J |  |  |  | A |  |  |  |  | S |  |  |  | O |  |  |  | N |  |  |  |  | D
|  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
OVERALL SUMMARY TOTAL BY PHASES | Hours
Phase 1 - Design Review and Contract Documents | 0
Phase 2 - Construction | 0
Phase 3 - Project Commissioning, Deficiency Review, Close-out | 0
TOTAL HOURS | 0